## SOP Checklist
Progress |  | 55%
Phase | Document | Status
Pre-Kick Off | Contract | TRUE
Project Initiation | Kick off Deck | TRUE
| Project Management Plan (Optional) | TRUE
Project Controls | Meeting Minutes | TRUE
| Timeline | TRUE
| Weekly Report | TRUE
| Risk Log | TRUE
| Issue Log | TRUE
| Change Request (CR) document (if necessary) | TRUE
System Integration Test (SIT) | SIT checklist | TRUE
User Requirement Study (URS) | URS Documentation | TRUE
User Acceptance Test (UAT) | UAT Script | FALSE
| Defect Log | FALSE
System Go Live | Go-Live Checklist | FALSE
Knowledge Transfer | KT Documentations | FALSE
Project Closure | Project Closure Deck | FALSE
| Project Closure Report | FALSE
| Certificate of Completion Optional) | FALSE
Support | Support Framework | FALSE
| SLA Report (AMS Project) | FALSE

## Project SOP
Pre Sales/ Sales | Project Team | All | Support | Ad Hoc
Request for Information
Request for Quotation
Request for Proposal
Receiving Purchase Order (PO)
Contract Formation & Finalization
Project Kick-Off
Platform Set Up
User Requirement Study
Project Development
System Integration Test (Optional)
User Acceptance Test
System Go Live
Knowledge Transfer
Post Implementation Support
Project Closure
Change Request
Invoice (According to Project Milestone)
Timeline Extension
Postmortem Evaluation
To involve Steering Committee
External Pre-Kickoff
Internal Pre-Kickoff

## Internal Pre-Kick Off
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Alt Text
P100 | Start | P200 |  | Start
P200 | Briefing by Presales & Sales | P300 |  | Process
P300 | Internal Project Alignment | P400 |  | Process
P400 | End |  |  | End
| Stage | Task | Details | PIC | Link to Template
| Internal | Briefing by PreSales & Sales | The Sales team briefs the Project team on commitments made to the client. | Sales Team | NA
|  |  | If a Pre-Sales team previously built a pilot project, a sharing session is conducted conducted. | Presales Team | NA
|  | The project team carries out internal alignment. | - The Project team reviews LOA/PO details to ensure alignment with prior discussions. - If discrepancies exist, initiate a scope clarification meeting with the client. | Project Team | NA
|  |  | - Sales, Presales and Project teams collaborate to finalize the project scope, deliverables, and timeline. Internal project alignment on: - Scope, deliverables, and constraints. - Identify key project risks and dependencies, other potential risks and mitigation strategies. - Resource allocation and key responsibilities. Proceed to "Contract Finalization" stage if contract is required for the project, if not then proceed to " External Pre- Kick Off" | Project Team Sales Team Presales Team | NA

## Contract Formation&Finalization
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Alt Text
P100 | Start | P200 |  | Start
P200 | Contract Formation & Compliance Check | P300 |  | Process
P300 | Contract Finalization & Sign-off | P400 |  | Process
P400 | External Pre-Kickoff |  |  | End
| Stage | Task | Details | PIC | Link to Template
| Contract Formation & Compliance Check | Draft the contract | The Sales team drafts the contract based on the finalized scope and client agreements. | Sales Team Project Team | NA | to have a checklist for contract checking
|  | Review key contract clauses | The Project team reviews key contract clauses, including: - Responsibilities and deliverables. - Service Level Agreements (SLAs) and penalties. - Payment terms and conditions. | Sales Team Project Team | NA
|  | Internal contract approval | Internal approval is obtained before proceeding. | Sales Team Project Team | NA
| Contract Finalization & Sign-off | Final review and alignment | Final review and alignment on contract terms with all stakeholders (Sales, Project, Client). | Sales Team Project Team | NA
|  | Secure approvals and signatures | Necessary approvals and signatures are secured. | Sales Team | NA
|  | Storing a copy of signed contract | The signed contract is stored in the project repository for reference. | Project Team | NA

## Contract Checklist
Contract Terms Checklist |  | 0%
Section | Item | Status
Agreement Period | Agreement Period | FALSE
| Extension of Agreement Period | FALSE
Project Scope | Objectives | FALSE
| Deliverables | FALSE
| Timeline | FALSE
| Roles and Responsibilities | FALSE
Pricing and Billing | Pricing Structures | FALSE
| Payment Terms | FALSE
| Late Payments and Penalties | FALSE
| Taxes and Additional Cost | FALSE
| Refunds and Adjustments | FALSE
Communication Plan | Communication Channels | FALSE
| Frequency of Communication | FALSE
| Reporting and Documentation | FALSE
Data Privacy and Protection | Personal Data | FALSE
| Data Confidentiality and Security Measures | FALSE
| Liability for Data Protection Breaches | FALSE
Risk Management Clauses | Risk Identification and Assessment | FALSE
| Risk Mitigation and Responsibilities | FALSE
| Contingency Plan | FALSE
| Force Majuere | FALSE
| Liabiliy and Indemnification | FALSE
Technology Specifications | Technology Stack | FALSE
| Security and Compliance | FALSE
SLA | Service Scope and Timeframe | FALSE
| Quality Metrics | FALSE
| Support and Maintenance | FALSE
| Exclusions | FALSE
| Service Credits | FALSE
| Penalties | FALSE
Termination Clauses | Early Termination of Services | FALSE
| Termination Conditions | FALSE
| Notice Period | FALSE
| Force Majuere | FALSE
| Dispute Resolution | FALSE
| Post-Termination Obligation | FALSE
Intellectual Property Rules | Confidentiality and Intellectual Property Protection | FALSE
| Licensing and Usage Rights | FALSE
Change Management | Scope of Change | FALSE
| Change Request Process | FALSE
| Impact Assessment | FALSE
| Review and Approval | FALSE
Approval and signatures | Approval Signatures | FALSE
| Date of Agreement | FALSE

## External Pre-Kick Off
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Alt Text
P100 | Start | P200 |  | Start
P200 | Project alignment with client | P300 |  | Process
P300 | End |  |  | End
| Stage | Task | Details | PIC | Link to Template
| External | The project team meets with the client to align expectations and finalize details. | Key discussion points: - Project scope, deliverables, and milestones. - Communication channels and escalation paths. - Role definitions and collaboration approach. - Potential risks and mitigation plans. - Date for project kick-off with clients | Project Team | Refer the project Kick off slides

## Project Kick Off
Process Step ID | Process Step Description | Next Step ID | Connector Label | Column1 | Shape Type | Alt Text
P100 | Initiation | P200 |  |  | Start
P200 | Project Planning & Controls | P300 |  |  | Process
P300 | Prepare Project Kick Off Deck | P400 |  |  | Process
P400 | Organize Internal Steer Co Meeting | P500 |  |  | Process
P500 | Formal Kick Off Meeting with Client |  |  |  | End
| Stage | Document/Task | Details | Internal/ External | PIC | Link to Template
| Project Planning | Timeline | Tasks and Activities: A list of all tasks and activities required to complete the project. Start and End Dates: The scheduled start and end dates for each task. Dependencies: Relationships between tasks, showing which tasks must be completed before others can begin. Milestones: Key achievements or deliverables that mark significant points in the project. Resource Allocation: Information on the resources assigned to each task. Progress Tracking: Indicators or markers to show the progress of each task. | Internal | Project Manager/ Tech Lead | 00_Project Timeline
|  | Organization Chart | Chart showing project team structure (both client and internal) Client's organization chart to be requested from client. | Internal | Project Manager | 01_Kick off
|  | Project Charter (Optional) | Formal document outlining project objectives and scope | External | Client | 01_Kick off
|  | Project Kick Off Deck | To be used at the project kickoff meeting to signify the start of the project. | External | Project Manager | 01_Kick off
|  | Project Management Plan | Comprehensive plan covering scope, schedule, and resources | External | Project Manager | 02_Project Management Plan
|  | Communication Plan | Strategy for stakeholder communication. Frequency: Determine how often updates will be provided (e.g., weekly, bi-weekly). Channels: Select appropriate communication channels (e.g., teams- best practice, whatsapp group etc). Content: Outline the type of information to be shared (e.g., progress reports, risk updates). | Internal | Project Manager | 01_Kick off
| Project Controls | Status Reports | Regular reports on project progress | External | Project Manager | 06_Weekly Project Meeting | 07_SteerCo Meeting
|  | Risk Log | A dynamic document that must be revisited and revised as the project progresses. Purpose: Provide detailed strategies for addressing each identified risk to minimize its impact on the project. Action: For each risk, outline the specific actions planned to mitigate or manage it. Include responsible parties, timelines for implementation, and any contingency plans if initial responses fail. | External | Project Manager/ Tech Lead | 05_Risk and Defects Logs
|  | Issue Log | Record of project issues and resolutions | External | Project Manager | 05_Risk and Defects Logs
|  | Change Requests | Documentation for any changes to project scope or plan | External | Change Control Board | 08_Change Request (CR)
|  | Meeting Minutes | Document the decisions made and actions agreed upon during the meeting. | External | Project Manager | 03_Meeting Minutes
|  | Delivery Tracking list | Documents to keep tracks if all required documents are in placed | Internal/ External | Project Manager | 04_Deliverables Tracking

## Platform Set Up
Platform | Set Up Steps | Prerequisites | Best Practices | Troubleshooting Tips | Online Resources | Installation Guide (Links)
Talend | 1. Download and Install. 2. Configure Talend Studio. 3. Create Projects. 4. Design ETL Processes. 5. Deploy Jobs. 6. Monitor and Maintain. | Java JDK installed. Appropriate user permissions. | Regularly update Talend. Document all transformations. Optimize ETL jobs for performance. | Check log files for errors. Verify database connections. Consult Talend Community for common issues. | Talend Help Center: https://help.talend.com/ Talend Open Studio for Data Integration Documentation: https://help.talend.com/r/en-US/7.14/data-integration-user-guide Talend Data Integration Guide: https://help.talend.com/r/en-US/7.14/data-integration-getting-started-guide Talend Cloud Documentation: https://help.talend.com/r/en-US/7.14/talend-cloud-documentation Talend Administration Center Documentation: https://help.talend.com/r/en-US/7.14/administration-center-user-guide Talend Community Forums: https://community.talend.com/ | NA
PowerBI | 1. Download and Install: Download Power BI Desktop or set up Power BI Service. 2. Connect Data Sources: Connect to various data sources within Power BI. 3. Create Reports: Develop reports and dashboards using Power BI Desktop. 4. Publish Reports: Publish reports to Power BI Service. 5. Set Up Workspaces: Organize and manage workspaces and datasets. 6. Configure Sharing and Security: Set up sharing options and security. 7. Monitor and Optimize: Track usage and optimize performance. | Power BI license. Data source access. | Use Power BI Service for collaboration. Optimize reports for performance. Regularly review access permissions | Check report performance. Verify data refresh schedules. Consult Power BI support for issues. | Power BI Documentation: https://docs.microsoft.com/en-us/power-bi/ Power BI Community: https://community.powerbi.com/ | NA
Tableau | 1. Download and Install: Download Tableau Desktop and/or Tableau Server/Online. 2. Configure Tableau Server: Set up Tableau Server if applicable, including user authentication and security. 3. Connect Data Sources: Set up connections to various data sources. 4. Create Workbooks: Design dashboards and reports in Tableau Desktop. 5. Publish and Share: Publish workbooks to Tableau Server/Online. 6. Set Up Permissions: Configure user permissions and access. 7. Monitor and Maintain: Regularly update and maintain Tableau Server. | Administrative access. Data source credentials. | Use extracts to improve performance. Regularly update Tableau. Secure Tableau Server. | Check Tableau logs for errors. Ensure proper data source connections. Review Tableau knowledge base for troubleshooting. | Tableau Documentation: https://help.tableau.com/current/pro/desktop/en-us/help.htm Tableau Community Forums: https://community.tableau.com/s/ | NA
QlikSense | 1. Download and Install: Download Power BI Desktop or set up Power BI Service. 2. Connect Data Sources: Connect to various data sources within Power BI. 3. Create Reports: Develop reports and dashboards using Power BI Desktop. 4. Publish Reports: Publish reports to Power BI Service. 5. Set Up Workspaces: Organize and manage workspaces and datasets. 6. Configure Sharing and Security: Set up sharing options and security. 7. Monitor and Optimize: Track usage and optimize performance. | QlikSense license. System requirements met. | Regularly back up data. Use data reduction techniques. Monitor app performance. | Check QlikSense logs. Verify data load scripts. Consult Qlik Community for help. | QlikSense Documentation: https://help.qlik.com/en-US/sense/ Qlik Community Forums: https://community.qlik.com/ | NA
Tagetik | 1. Installation: Follow the installation guide for Tagetik (on-premises or cloud-based). 2. Initial Configuration: Set up system configurations and user access. 3. Data Integration: Connect to source systems and import data. 4. Model Setup: Define financial models and business processes. 5. Testing: Validate the setup with test data. 6. Training: Train users on Tagetik functionalities. 7. Deployment: Go live with the implemented solution. | Database access. System requirements met. | Regularly backup configurations. Maintain updated documentation. Follow best practices for financial modeling. | Monitor system performance. Ensure data integrity. Contact Tagetik support for complex issues. | Tagetik Support and Documentation: https://www.tagetik.com/en/resources/documentation Tagetik Community: https://community.tagetik.com/ | NA
Snowflake | 1. Sign Up: Create a Snowflake account and choose a cloud provider. 2. Configure Environment: Set up Snowflake environment, including warehouses, databases, and schemas. 3. Connect Data Sources: Establish connections to external data sources. 4. Load Data: Load data into Snowflake using Snowpipe or bulk loading. 5. Develop Queries: Write and optimize SQL queries. 6. Set Up Security: Configure user roles and access permissions. 7. Monitor and Optimize: Monitor performance and manage resources. | Snowflake account. Cloud provider setup. | Use data partitioning for performance. Regularly review and optimize queries. Document all configurations. | Check Snowflake query history. Verify data loading processes. Contact Snowflake support for complex issues. | Snowflake Documentation: https://docs.snowflake.com/ Snowflake Community: https://community.snowflake.com/ | NA
RapidMiner | 1. Download and Install: Download and install RapidMiner Studio or Server. 2. Configure Environment: Set up the environment and data connections. 3. Design Workflows: Create and configure data science workflows. 4. Train Models: Build and train predictive models. 5. Evaluate Models: Test and validate model performance. 6. Deploy Models: Deploy models for production use. 7. Monitor and Update: Continuously monitor and update models. | Java Runtime Environment. Appropriate licensing. | Use data preprocessing techniques. Document workflows. Regularly update RapidMiner. | Check execution logs. Verify data connections. Consult RapidMiner Community for issues. | RapidMiner Documentation: https://docs.rapidminer.com/ RapidMiner Community Forum: https://community.rapidminer.com/ | NA
UiPath | 1. Download and Install. 2. Configure Orchestrator. 3. Develop Automation. 4. Test Workflows. 5. Deploy to Orchestrator. 6. Monitor and Maintain. | UiPath license. Orchestrator setup. | Follow UiPath best practices for workflow design. Document all automation processes. Regularly update UiPath software. | Check Orchestrator logs. Verify robot connectivity. Consult UiPath Forum for common issues. | UiPath Documentation: https://docs.uipath.com/ UiPath Community Forum: https://forum.uipath.com/ | NA

## SIT
| Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Alt Text
| 1 | Test Planning/ Set Up | 2 |  | Process
| 2 | Development | 3 |  | Process
| 3 | Test Execution (Internal) | 4 |  | Process
| 4 | Defect Management | 5 |  | Process
| 5 | UAT Deployment |  |  | End
Step | Section | Action | Link to template
1 | Test Planning | Develop a test plan, define objectives, identify test cases, and set up the test environment. | SIT Whenever there is a platform setup, please prepare the SIT - test plan, test scripts, and sign off.
2 | Setup | Configure the test environment, deploy integrated components, and ensure necessary data and tools are available.
3 | Development | Develop detailed test cases covering all integration points, including positive, negative, and edge cases.
4 | Test Execution | Execute test cases, document results, and track defects or issues.
5 | Defect Management | Prioritize, assign, and resolve defects. Retest resolved issues and update defect log.
6 | UAT Deployment | Review SIT outcomes with stakeholders, obtain sign-off to proceed to the next phase (e.g., UAT).

## URS
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Alt Text
P100 | Identify (1) Business Users for each Sprint (2) How many workshops | P200 |  | Start
P200 | Schedule Meetings | P300 |  | Process
P300 | Organize and Conduct Workshops | P400 |  | Process
P400 | URS Documentation | P500 |  | Process
P500 | Finalize and Obtain Approval and Sign off from client |  |  | End
Project Type | Description | URS | Link to Template
Dashboard | A visual representation of key performance indicators (KPIs) and metrics, often created using tools like Power BI/ Tableau/ QlikSense. Dashboards provide interactive and real-time insights into business performance. | (1) Define key metrics and KPIs (2) Identify target audience and user needs (3) Determine data sources and integration requirements (4) Specify design preferences and interactivity features (5) Prepare Dashboard Wireframe | BI
ETL (Extract, Transform, Load) | A process that involves extracting data from various sources, transforming it into a suitable format, and loading it into a target system, such as a data warehouse. ETL processes are essential for data integration and preparation. | (1) Identify data sources and formats (2) Define transformation rules and logic (3) Determine data loading requirements and schedules (4) Specify data quality and validation rules | DE
Data Warehouse | A centralized repository that stores integrated data from multiple sources, optimized for query and analysis. Data warehouses support business intelligence and reporting by consolidating historical and current data. | (1) Identify data sources and integration needs (2) Define data modeling and schema requirements (3) Specify performance and scalability needs (4) Determine data retention and archiving policies | DW
Data Science | The application of statistical analysis, machine learning, and algorithms to extract insights and knowledge from data. Data science projects often involve predictive modeling, data mining, and advanced analytics. | (1) Define business objectives and problems to solve (2) Identify relevant data sets and features (3)Specify modeling and analytical techniques (4) Determine evaluation metrics and success criteria | DS
RPA (Robotic Process Automation) | The use of software robots or "bots" to automate repetitive, rule-based tasks and processes. RPA improves efficiency and reduces human error by automating tasks such as data entry, process standardization, and reporting. | (1) Identify processes and tasks to automate (2) Define rules and decision-making criteria (3) Determine integration points with other systems (4) Specify user interaction and exception handling requirements | RPA
CPM (Tagetik) | A software solution for enterprise performance management (EPM), including financial planning, budgeting, and reporting. Tagetik integrates financial data and provides tools for consolidation, planning, and analysis. | (1) Define financial planning and reporting requirements (2) Identify data sources and integration needs (3) Identify dimensions needed to be set up (4) Specify consolidation and budgeting rules (5) Determine user roles and access controls | Tagetik

## UAT
| Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Alt Text
| 1 | UAT Planning | 2 |  | Start
| 2 | UAT Environment Set Up | 3 |  | Process
| 3 | UAT Test Case Development | 4 |  | Process
| 4 | UAT Execution | 5 |  | Process
| 5 | Defect Management | 6 |  | Process
| 6 | UAT Sign-Off | 7 |  | Process
| 7 | Prepare for Go-Live |  |  | End
Step | Section | Input | Action | Output
1 | UAT Planning | Project requirements, system design, and SIT outcomes. | Develop a UAT plan, define test objectives, identify key test cases, and select UAT participants. | Approved UAT plan.
2 | UAT Environment Setup | UAT plan, system architecture. | Configure the UAT environment, ensuring it mirrors the production environment as closely as possible. | Ready UAT environment.
3 | UAT Test Case Development | User requirements, business processes, and use cases. | Develop UAT test cases based on real-world scenarios, ensuring they cover all critical functionalities. | UAT test case documents/ UAT Script
4 | UAT Execution | UAT test cases, ready UAT environment. | Execute UAT test cases with end users, document results, and report any issues encountered. | UAT execution reports, feedback logs.
5 | Defect Management | Feedback and issue logs from UAT execution. | Prioritize, assign, and resolve issues identified during UAT. Retest resolved issues and update logs. | Updated issue logs, resolved issues.
6 | UAT Sign-Off | UAT execution reports, resolved issue logs. | Review UAT results with stakeholders and end users. Obtain formal sign-off indicating acceptance. | UAT sign-off document, approved for deployment.
7 | UAT Closure/Report (Optional) | UAT sign-off document. | Archive UAT documents, including test cases, logs, and reports. Conduct a post-UAT review session. | UAT closure report, lessons learned.
| Platform | Link to UAT Script Template | Remarks
| Talend | DE | -
| BI | BI | -
| Tagetik | Tagetik | -
| Snowflake | DE | Refer DE - Talend project templates
| RapidMiner | DS | Pure Data Science projects need to provide the modelling summary to evaluate all the built models. Refer the technical and final reports sample to finalize the contents of the testing based on projects requirements
| UiPath | RPA | -

## Go-Live
| Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Alt Text
| 1 | Pre-Go Live Checklist | 2 |  | Start
| 2 | Communication Plan | 3 |  | Process
| 3 | Deployment Plan Execution | 4 |  | Process
| 4 | System Verification | 5 |  | Process
| 5 | Post-Go-Live Monitoring | 6 |  | Process
| 6 | Issue Management |  |  | End
Step | Section | Input | Action | Output | Link to templates
1 | Pre-Go-Live Checklist | UAT sign-off document, deployment plan. | Review and complete the pre-go-live checklist, ensuring all prerequisites are met (e.g., backups, approvals). | Completed pre-go-live checklist, approvals in place. | Delivery Checklist
2 | Communication Plan | Go-Live date, stakeholder list. | Develop and distribute a communication plan to inform all relevant stakeholders about the Go-Live timeline and activities. | Communication plan and notifications sent to stakeholders.
3 | Deployment Plan Execution | Deployment plan, system configuration, release notes. | Execute the deployment plan according to the schedule, ensuring all components are deployed as per the plan. | Deployed system components, deployment log.
4 | System Verification | Deployed system, system verification checklist. | Perform system verification to ensure that the deployment was successful and all services are functioning correctly. | System verification report, confirmation of successful deployment.
5 | Post-Go-Live Monitoring | Live system, monitoring tools. | Monitor the system post-deployment to identify and resolve any issues that arise immediately after go-live. | Monitoring reports, issue logs, resolved issues.
6 | Issue Management | Issues identified during post-go-live monitoring. | Prioritize, assign, and resolve issues. Communicate critical issues to stakeholders and provide updates. | Updated issue logs, resolved critical issues.

## KT
| Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Alt Text
| 1 | Preparation for KT | 2 |  | Start
| 2 | Develop Training Materials | 3 | Yes,No | Process
| 3 | Conduct KT Sessions | 4 |  | Process
| 4 | Hands on Training and Demo | 5 |  | Process
| 5 | Documentation Handover | 6 |  | Process
| 6 | Client Review and Sign Off |  |  | End
Step | Section | Input | Action | Output
1 | Preparation for Knowledge Transfer | Go-Live documentation, system documentation, training materials. | Identify the knowledge areas to be transferred, prepare relevant documentation, and schedule KT sessions. | Comprehensive list of KT topics, scheduled KT sessions.
2 | Develop Training Materials | System documentation, user manuals, FAQs, SOPs. | Create or update training materials tailored to the needs of the operations and support teams. | Finalized training materials.
3 | Conduct Knowledge Transfer Sessions | Training materials, list of participants. | Conduct KT sessions with the operations, support, and maintenance teams, ensuring all critical areas are covered. | Completed KT sessions, attendance records.
4 | Hands-On Training and Demonstrations | Live system, training environment. | Provide hands-on training and live demonstrations to ensure practical understanding of the system. | Hands-on experience, resolved queries from participants.
5 | Documentation Handover | Finalized system documentation, training materials. | Handover all relevant documentation, including system design, operational procedures, and troubleshooting guides, to the support teams. | Successful handover of documentation.
6 | Review and Sign-Off | Completed KT sessions, feedback report. | Review the KT process with stakeholders and obtain sign-off indicating successful knowledge transfer. | KT sign-off document
| Platform | Link to Sample KT Document
| Talend | DE
| BI | BI
| Tagetik | Tagetik
| Snowflake | DE
| RapidMiner | DS
| UiPath | RPA

## Closure
| Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Alt Text
| 1 | Final Deliverable Review | 2 |  | Start
| 2 | Prepare Project Closure Slide | 3 |  | Process
| 3 | Billing Closure | 4 |  | Process
| 4 | Internal Meeting | 5 |  | Process
| 5 | Project Closure Meeting |  |  | End
Step | Section | Action | Output | Link to Templates
1 | Final Deliverable Review | Review all project deliverables to ensure they meet the agreed-upon specifications and quality standards. | Verified deliverables, approval for completion. | 10_Project Closure
2 | Prepare Project Closure Slide | The slide should effectively communicate the status of the project, highlight achievements, and outline any remaining actions or considerations. *Insert link to project closure template | Draft Project Closure Deck
3 | Billing Closure | Review and close out all financial aspects of the project (invoicing) | Summary of invoice issued against milestone payments and outstanding bililng (if any)
4 | Internal Meeting | Review Project Closure Deck Customer success activies - fol | Finalized Project Closure Deck
5 | Project Closure Meeting | Schedule the meeting with the client and ensure that all relevant stakeholders from both sides are invited. Internal: Project Director, Project Team, Account Manager, Support External: Steering Committee, Project Team | Project Closure Report Summit the report after a project closure meeting. Project Closure report is a document that enumerates and describes the goals and objectives of a project, as well as specifies when it was fully completed.

## Post Mortem
Note: | The internal post-mortem review can be conducted during the internal discussion for project closure or as a separate session
| Key Topics to be Covered | Objective | Action | Output
| Review Project Objectives and Outcomes | Revisit the project’s initial objectives and compare with actual outcomes. | Discuss whether the project met its goals, delivered expected outcomes, and adhered to the agreed scope. | Comparison of objectives vs. outcomes.
| Analyze Successes | Identify what went well and contributed to the project’s successes. | Discuss successful strategies, effective processes, and positive contributions from team members. | Documented successes and effective practices.
| Identify Challenges and Issues | Highlight areas where the project faced difficulties or did not meet expectations. | Review issues, delays, and challenges encountered during the project lifecycle. Discuss their impact and resolution. | Documented challenges, issues, and their impacts.
| Evaluate Project Management | Assess the effectiveness of project management practices. | Review project management processes, tools, and techniques used. Discuss their effectiveness and areas for improvement. | Evaluation of project management practices.
| Gather Feedback from Team Members | Collect feedback from all team members about their experiences. | Conduct surveys or open discussions to gather input on team dynamics, communication, and individual experiences. | Collected feedback from project team members.
| Analyze Financial Performance | Review the project’s financial performance. | Compare actual expenses with the budget, identify financial discrepancies, and assess financial management practices. | Analysis of financial performance and budget adherence.

## Support
Section | Objective | Action | Output
Setup Support Structure | Establish the framework for post-implementation support. | Define support team roles, responsibilities, and escalation paths. Ensure all necessary tools and systems are in place. | Established support structure and resources.
Handle Support Requests | Address and resolve support requests and issues from users. | Set up a system for logging, tracking, and managing support requests. Assign and prioritize issues based on severity and impact. | SLA Report

## CR
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Alt Text
1 | Receive New Requirement | 2 |  | Start | Situation occurs when clients requirements might not be within the scope of project or additional requirements occur after URS signed off
2 | Initial Review (Within Project Team) | 3 |  | Process | Project team to assess whether the change request is within the current project scope or if it represents a significant deviation that would require scope adjustment. Project team to assess effort/ cost/ resources needed to complete the additional requirement.
3 | Is Requirement Clear? | 4,5 | Yes,No | Decision | Steering Committee to decide if requirements falls within the scope of project or constitutes a change request
4 | Impact Analysis | 6 |  | Process | Amend URS document to document down new requirements. Get client to sign off amended URS document to align on expectations.
5 | Request Clarification from Client | 3 |  | End
6 | Internal Steering Committee Discussion | 7 |  | Process
7 | To classify as CR? | 8,9 | Yes, No | Decision
8 | Prepare Change Request Documentation | 10 |  | Process
9 | Update Project Plan | 14 |  | Process
10 | Client Approval | 11 |  | Process
11 | Contract and Invoice Preparation | 12 |  | Process
12 | Client Sign Off CR | 13 |  | Process
13 | Implement Change |  |  | End
14 | Implement the requirement as part of the existing project |  |  | End
Link to template
Change Request | 08_Change Request (CR)

## Timeline Extension
| Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Alt Text
| 1 | Identify the Need for an Extension | 2 |  | Start
| 2 | Impact Analysis | 3 |  | Process
| 3 | Internal Discussion and Decision | 4 |  | Process
| 4 | Draft Timeline Extension Request | 5 |  | Process
| 5 | Internal Approval | 6 |  | Process
| 6 | Submit the Request to Client | 7 |  | Process
| 7 | Client Discussion and Negotiation | 8 |  | Process
| 8 | Document and Update Project Plan | 9 |  | Process
| 9 | Monitor and Report Progress |  |  | End
Step | Section | Action | Output
1 | Identify the Need for an extension | Trigger: Project is behind schedule due to unforeseen issues. PM gathers data on project status. | Update project tracking system.
2 | Impact Analysis | Assess the impact on the project’s timeline, budget, and resources. | Impact Analysis
3 | Internal Discussion and Decision | Convene a meeting with stakeholders to discuss the impact analysis and align on the proposed new timeline and resource needs | Decision on Timeline Extension
4 | Submit the Request to the Client | Send the approved request to the client. Request a meeting or call if needed. | Record of communication sent to the client.
5 | Client Discussion and Negotiation | Discuss and negotiate the extension with the client. Address any concerns and adjust the timeline if necessary. | Agreement on the new timeline.
6 | Document and Update Project Plan | Update the project plan, timelines, and documents. Communicate the updated timeline to all stakeholders. | Updated project plan and timeline.
7 | Monitor and Report Progress | Monitor progress to ensure adherence to the new time. Provide regular status updates to the client. | Ongoing progress reports.
Link to template
| Extension of Time (EOT) | 09_Extension of Time (EOT)