## Slide 1: TIME CSET Project
Prepared by: Amirun Fadzli

## Slide 2: Executive Summary
• Strategic data and application modernization
• 9 milestones from planning to support
• Each milestone includes tasks, outputs, and steps
• Goal: Seamless implementation and stakeholder alignment

## Slide 3: Project Roll-Out
• Refine Project Scope & Implementation Planning: Finalized scope and plan
→ Review charter → Conduct interviews → Draft scope → Validate and sign-off

## Slide 4: Project Kick-Off
• Aligned stakeholders: Prepare deck → Schedule meeting → Conduct and document

## Slide 5: Phase 1a – Platform Readiness
• Technical Requirement Study: Documented technical needs
→ Workshops → Gather needs → Document → Validate
• Technical Architecture Design & Planning: Approved architecture
→ Design blueprint → Define stack → Review and sign-off
• User Requirement Study (URS): Finalized URS document
→ Interviews → Use cases → Document → Validate
• Enterprise Data Platform Setup: Operational platform
→ Provision infra → Configure → Validate
• System Integration Test (SIT): Verified system integration
→ Develop test cases → Execute → Log issues → Sign-off

## Slide 6: Phase 1b – Raw Layer ETL
• MDI Framework Design (Raw): MDI blueprint
→ Define metadata → Design flow → Document
• Control Tables Development: Populated control tables
→ Gather input → Design schema → Populate → Validate
• Data Pipeline Dev (Files): File ingestion pipelines
→ Identify sources → Develop → Test
• Data Pipeline Dev (RDBMS): RDBMS ingestion pipelines
→ Identify DBs → Develop → Test
• User Acceptance Test (UAT): UAT sign-off
→ Prepare cases → Conduct → Resolve → Sign-off
• Technical Documentation: Complete documentation
→ Document logic → Include recovery → Publish

## Slide 7: Phase 1c – Harmonized Layer ETL
• MDI Framework Design (Harmonized): Harmonized MDI framework
→ Analyze metadata → Define rules → Document
• Data Pipeline Development: Functional transformation pipelines
→ Define logic → Develop → Test
• User Acceptance Test (UAT): UAT sign-off
→ Prepare → Conduct → Resolve → Sign-off
• Historical Data Migration: Migrated historical data
→ Identify sources → Migrate → Validate
• Technical Documentation: Complete documentation
→ Document rules → Review → Publish

## Slide 8: Phase 1d – Data Mart Layer
• Data Mart Design: Data mart schema
→ Define requirements → Design schema → Review
• Data Mart Development: Populated data marts
→ Develop ETL → Validate → Review
• User Acceptance Test (UAT): UAT sign-off
→ Prepare → Conduct → Resolve → Sign-off
• Technical Documentation: Complete documentation
→ Document schema → Include tuning → Publish

## Slide 9: Phase 1e – Data Catalogue
• Design Governance & Quality: Governance framework
→ Define roles → Establish metrics → Document
• Build Data Catalogue: Searchable catalogue
→ Select tool → Ingest metadata → Validate
• User Acceptance Test (UAT): UAT sign-off
→ Prepare → Conduct → Resolve → Sign-off
• Technical Documentation: Complete documentation
→ Document setup → Include guide → Publish

## Slide 10: Phase 1f – App Modernization
• UI/UX Design & Verification: Approved designs
→ Research → Wireframes → Review → Finalize
• High/Low Level Design Docs: Detailed design docs
→ Draft architecture → Develop logic → Review
• Sprint 1–4 Modernization: Delivered features
→ Plan → Develop → Review → Demo
• UAT Part 1–4: UAT sign-off
→ Prepare → Conduct → Resolve → Sign-off

## Slide 11: Phase 1g – Post Implementation
• Production Deployment: Live system
→ Validate → Deploy → Monitor
• System Go Live: Operational system
→ Announce → Enable access → Monitor

## Slide 12: Next Steps / Q&A
• Finalize documentation
• Share with stakeholders
• Prepare for support phase
• Open for feedback and questions